## Information
GUIDE ON HOW TO FILL IN THE TEMPLATE
In order to fill in the APP template you must save it in MS XLS or XLSX format
DO NOT change the template's format
DO NOT change the order of columns
DO NOT change the column headers
DO NOT leave empty rows
Fields in red highlight indicate mandatory fields, while fields in yellow highlight indicate fields that are optional
Cells B1-B7 are optional and must be filled in manually
If uncertain or requiring help, please consult the Buyer User Manual
The rules to complete the template for creating a valid APP are listed below
Fill in the "Data" sheet of the APP template starting from Row 11
Field | Validation Type
Class | Mandatory, values: Goods, Works, Non Consulting Services, Consulting Services
UNSPSC | Mandatory, 8 digit UNSPSC Code
IFMIS GL Account | Mandatory
Description | Mandatory
Ref No | Mandatory, use by MDA
Project Code | Optional, for Project Procurement tracking
Unit of Measure | Optional
Quantity | Optional
ZMW Estimated Budget - GOZ | Mandatory
ZMW Estimated Budget - Other | Optional
ZMW Estimated Budget - Total | Mandatory
$FX Budget Amount - Currency | Optional
$FX Budget Amount - Amount | Optional
Source of Funds | Optional
Prequalification (Y/N) | Mandatory
Procurement Method | Mandatory, values: OBN, OBI, OSN, OSI, LBN, LBI, LSN, LSI, SB, DB
Estimated Dates - Publication | Mandatory
Estimated Dates - Award | Optional
Estimated Dates - Start | Mandatory
Public View | Mandatory, values: Y, N
Public View Justification | Mandatory when Public View is set to 'N'
Comments | Optional
Source | Used to point either to a corresponding Budget Data Package, or to a machine or human-readable source where users can find further information on the budget line item identifiers, or project identifiers, provided here
Project ID | An external identifier for the project that this contracting process forms part of, or is funded via (if applicable). Some organizations maintain a registry of projects, and the data should use the identifier from the relevant registry of projects.
URI | A URI pointing directly to a machine-readable record about the related budget or projects for this contracting process.
Rationale | The rationale for the procurement provided in free text. More detail can be provided in an attached document.
Type of Entry | Blank for initial entries in the APP, A for additional entry and M for modification of an existing entry

## data
Entity | Misenge Environmental and Technical Services Limited
Procurement Plan for year | 2021
Version | 2
Procurement Budget | 3537667
ZMW Control Total
Date Last Updated | 2021-01-15
Comments
The authority may please note that METS was awarded a works contract necessitating the need to update the plan.
[8 empty] | ZMW Estimated Budget |  |  | FX Budget Amount |  |  |  |  | Estimated dates
Class | UNSPSC | IFMIS GL Account | Description | Ref No | Project Code | Unit of Measure | Quantity | GOZ | Other | Total | Currency | Amount | Source of Funds | Prequalification (Y/N) | Procurement Method | Publication | Award | Start | Public View (Y/N) | Public View Justification | Comments | Source | Project ID | URI | Rationale | Type of Entry
Goods | 43211500 | 0 | Supply and Delivery of computers/ Printers and a projector | 0 | 0 | each | 14 | 0 | 406608 | 250608 | 0 | 0 | METS Budget | N | SB | 2021-02-10 | 2021-02-24 | 2021-02-03 | Y
Goods | 26111600 | 0 | Supply and Delivery of a genset | 0 | 0 | each | 1 | 0 | 200000 | 200000 | 0 | 0 | METS Budget | N | SB | 2021-07-26 | 2021-08-02 | 2021-08-09 | Y
Goods | 24111810 | 0 | Supply and installation of a 5000Ltr water tank | 0 | 0 | each | 1 | 0 | 12000 | 12000 | 0 | 0 | METS Budget | N | SB | 2021-07-26 | 2021-08-02 | 2021-08-09 | Y
Goods | 41000000 | 0 | Supply and Delivery of Laboratory apparatus | 0 | 0 | each | 8 | 0 | 205000 | 205000 | 0 | 0 | METS Budget | N | SB | 2021-07-26 | 2021-08-02 | 2021-08-09 | Y
Goods | 22101901 | 0 | Supply and Delivery of 1 poker vibrator and 1 concrete mixer | 0 | 0 | each | 2 | 0 | 145750 | 145750 | 0 | 0 | METS Budget | N | SB | 2021-04-05 | 2021-04-12 | 2021-04-19 | Y
Goods | 41114200 | 0 | Supply and Delivery of environmental survey equipment | 0 | 0 | each | 5 | 0 | 341662 | 341662 | 0 | 0 | METS Budget | N | SB | 2021-04-05 | 2021-04-19 | 2021-04-26 | Y
Goods | 44000000 | 0 | Supply and delivery of office equipment- legal/HR | 0 | 0 | each | 3 | 0 | 10310 | 10310 | 0 | 0 | METS Budget | N | SB | 2021-03-01 | 2021-03-08 | 2021-03-15 | Y
Non consulting services | 73152103 | 0 | Framework agreement- servicing of equipment at the METS laboratory | 0 | 0 | each | 16 | 0 | 200000 | 200000 | 0 | 0 | METS Budget | Y | SB | 2021-02-15 | 2021-02-22 | 2021-03-01 | Y
Consulting services | 80111614 | 0 | Framework agreement- consultants for engineering jobs | 0 | 0 | each | 2 | 0 | 300000 | 300000 | 0 | 0 | METS Budget | Y | SB | 2021-02-15 | 2021-02-22 | 2021-03-01 | Y
Consulting services | 77000000 | 0 | Framework agreement - consultants to provide environmental jobs | 0 | 0 | each | 3 | 0 | 300000 | 300000 | 0 | 0 | METS Budget | Y | SB | 2021-02-15 | 2021-02-22 | 2021-03-01 | Y
Goods | 41121800 | 0 | Frame work agreement - laboratory consumables | 0 | 0 | each | 5 | 0 | 521300 | 521300 | 0 | 0 | METS Budget | Y | OBN | 2021-02-22 | 2021-03-29 | 2021-04-12 | Y
Non consulting services | 84131500 | 0 | Frame work agreement- provision of insurance and life assurance services | 0 | 0 | each | 2 | 0 | 182424 | 182424 | 0 | 0 | METS Budget | Y | SB | 2021-10-04 | 2021-10-18 | 2021-11-01 | Y
Goods | 14111509 | 0 | Framework agreement - supply and delivery of stationery | 0 | 0 | each | 1 | 0 | 72538 | 72538 | 0 | 0 | METS Budget | Y | SB | 2021-03-01 | 2021-03-15 | 2021-03-29 | Y
Non consulting services | 78180100 | 0 | Frame work agreement- servicing of motor vehicles | 0 | 0 | each | 4 | 0 | 248880 | 248880 | 0 | 0 | METS Budget | Y | SB | 2021-03-01 | 2021-03-15 | 2021-03-29 | Y
Non consulting services | 81112200 | 0 | Framework agreement- computer service maintenance and repairs | 0 | 0 | each | 20 | 0 | 33270 | 33270 | 0 | 0 | METS Budget | Y | SB | 2021-03-01 | 2021-03-15 | 2021-03-29 | Y
Goods | 53000000 | 0 | Supply and delivery of PPE | 0 | 0 | each | 1 | 0 | 11550 | 11550 | 0 | 0 | METS Budget | Y | SB | 2021-06-07 | 2021-06-14 | 2021-06-21 | Y
Goods | 41000000 | 0 | Supply and Delivery of certified reference materials | 0 | 0 | each | 1 | 0 | 46375 | 46375 | 0 | 0 | METS Budget | Y | SB | 2021-08-02 | 2021-08-16 | 2021-08-30 | Y
Works | 71121407 | 0 | Equiping,siting and drilling of boreholes | 0 | 0 | each | 3 | 0 | 300000 | 300000 | 0 | 0 | METS Budget | N | SB | 2021-02-16 | 2021-03-02 | 2021-03-09 | Y
Goods | 15000000 | 0 | Framework agreement - supply and delivery of fuel/lubricnts | 0 | 0 | each | 1 | 0 | 143820 | 143820 | 0 | 0 | METS Budget | Y | DB | 2021-02-19 | 2021-02-26 | 2021-03-12 | Y
Works | 71161413 | 0 | Fabrication and installation of tank stand, hoisting 10000ltr tank | 0 | 0 | each | 1 | 0 | 61000 | 61000 | 0 | 0 | METS Budget | Y | SB | 2021-02-26 | 2021-03-03 | 2021-03-10 | Y
Goods | 30180000 | 0 | Supply and Delivery of material requirements for the installation and fabrication of the tank stand | 0 | 0 | each | 1 | 0 | 42000 | 42000 | 0 | 0 | METS Budget | Y | SB | 2021-02-26 | 2021-03-03 | 2021-03-10 | Y
Non consulting services | 80111604 | 0 | Hire of Laboratory technicians | 0 | 0 | each | 2 | 0 | 52000 | 52000 | 0 | 0 | METS Budget | Y | SB | 2021-02-26 | 2021-03-03 | 2021-03-10 | Y